# Work plan
## Deadlines
- 2022-03-06 Choose a project proposal and send your choice via email to epsatisep@gmail.com
- 2022-03-16 Define the Project Backlog (what must be done and key deliverables - every member should preferably participate in every task), Global Sprint Plan, Initial Sprint Plan (which tasks should be included, who does what) and Release Gantt Chart of the project and insert them on the wiki (planning)
- 2022-03-23 Upload the “black box” System Diagrams & Structural Drafts to the wiki
- 2022-04-06 Upload the List of Components and Materials (what & quantity) to the wiki *
- 2022-04-12 Upload the detailed System Schematics & Structural Drawings to the wiki and do the cardboard scale model of the structure
- 2022-04-14 Upload the Interim Report and Presentation to the wiki. The report must contain the the following chapters: Introduction, Project Management, State of the Art, Marketing Plan, Eco-efficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography. In particular, the Project Management chapter includes the updated project progress register, the sprint report for completed sprints (tasks that were included, statuses, assignees, allocations) and the updated release Gantt chart
- 2022-04-21 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks
- 2022-04-27 Upload the final List of Materials (local providers & price, including VAT and transportation) and the 3D Model Video to the wiki
- 2022-05-14 Upload refined Interim Report (based on Teacher & Supervisor Feedback)
- 2022-05-26 Upload packaging solution to Deliverables and Report
- 2022-06-07 Upload the results of the Functional Tests to the wiki
- 2022-06-07 Upload the results of the Functional Tests to the wiki
- 2022-06-18 Upload the Final Report, Presentation, Video, Paper, Poster and Manual
- 2022-06-23 Final Presentation, Individual Discussion and Assessment
- 2022-06-28:
  - Update the wiki, report, paper with all suggested corrections
  - Place in the files section of the MS Teams channel of your team a folder with the refined deliverables (source + PDF) together with all code and drawings produced
  - Hand in to the EPS coordinator a printed copy of the refined report and poster
- 2022-06-30:
  - Hand in the prototype and user manual to the client
  - Do a live demo of the prototype
  - Receive the EPS@ISEP certificate
  - Bring and share typical food from your country
## Project Plan
Define your optimal sprint duration and plan your sprints until project end using Global Sprint Plan Table .
Global Sprint Plan
Sprint Start Finish / 0 10/03/2022 23/03/2022 / 1 24/03/2022 07/04/2022 / 2 08/03/2022 20/04/2022 / 3 21/04/2022 04/05/2022 / 4 05/05/2022 18/05/2022 / 5 19/05/2022 01/06/2022 / 6 02/06/2022 15/06/2022 / 7 16/06/2022 29/06/2022

Build your project backlog, including all relevant tasks/deliverables, using Project Backlog Table . Prioritize all backlog items (PBI), keeping higher priority items at the top, and lower priority at the bottom.
Project Backlog
PBI Sprint 0 Title Status / A Deadline: Define Project Backlog, Global Sprint, Intial Sprint Plan, Gantt Chart Done: DEADLINE / B State of the art - Scientific To do / C State of the art - Commercial To do / D Do research & decide which insects we are going to use To do / E Do research & decide on which & how many differnt product outputs (pet feed, food, fertilizer) we want to produce To do / F Do research on lifecycle options and present on possibilities To do / G Decide final idea To do / H Make System Diagrams To do / I Make Structural Drafts To do / J Deadline: Upload the “black box” System Diagrams & Structural Drafts to the wiki To do: DEADLINE

Project Backlog
PBI Sprint 1 Title Status / Z Sample task To do / K Sample task To do / D Sample task To do / A Sample task To do / B Sample task To do / E Sample task To do / C Sample task To do

Plan each sprint at its beginning (Sprint Planning session) using the Sprint Plan Table F=Finn B=Benjamin L=Leonie P=Paul M=Marie .
Sprint Plan
Sprint Task Duration (d) Responsible Involved / 0 A 1 M and L F, B, L, P, M / 0 B 8 F,B and P F, B, L, P, M / 0 C 8 L and M F, B, L, P, M / 0 D 1 F, B, L, P, M F, B, L, P, M / 0 E 5 F, B, L, P, M / 0 F 5 F, B, L, P, M / 0 G 1 F, B, L, P, M / 0 H 3 F, B, L, P, M / 0 I 3 F, B, L, P, M / 0 J 1 F, B, L, P, M

Review each sprint at its end and update each item status on the Progress Register Table .
Project Progress Register
Sprint PBI Responsible Involved Status / 0 A M, L F, B, L, P, M Done / 0 B, C F, B, L, P, M F, B, L, P, M In progress / 1 F, B, L, P, M / 2 F, B, L, P, M / 3 F, B, L, P, M / 4 F, B, L, P, M / 5 F, B, L, P, M / 6 F, B, L, P, M

Identify key project deliverables (when they will be started and completed) and build a release Gantt chart. See Figure for inspiration.

Release Gantt chart
## Blackbox Diagram

Preliminary Blackbox Diagram
## Structural / Design Drafts

Structural_Design_Draft